## Summary
Workstream Summary — At a Glance
Auto-updated from detail tab ¦ April 01, 2026
Workstream | Total Milestones | Overall Status | Notes
Tagging & Naming Conventions | 3 | Not Started | Must finalize before deploying resources
Bootstrap TF Module | 5 | Not Started | Foundation — blocks everything else
Account Vending Machine | 4 | Not Started | Depends on Bootstrap + OU/SCP design
IAM Identity Center (SSO) | 5 | Not Started | IdP decision needed first
Security Account Setup | 7 | Not Started | Delegated admin for GuardDuty, Config, etc.
Shared Network Setup | 7 | Not Started | Depends on CIDR planning + TGW
EKS Baseline (CMMC) | 8 | Not Started | CMMC controls mapping critical
Landing Zone Team Onboarding | 6 | Not Started | Depends on EKS + Networking + Bootstrap
Budget & Cost Management | 5 | Not Started | Tags must be finalized first
Suggested Execution Order: Tagging → Bootstrap → Account Vending → IAM Identity Center → Security Account → Networking → EKS Baseline → Team Onboarding → Budget (parallel where possible)

## AWS Program Tracker
AWS Enterprise Landing Zone — Executive Status Tracker
Last Updated: April 01, 2026 ¦ Cadence: Biweekly ¦ Next Update: April 15, 2026 ¦ IaC: Terraform + GitHub Actions
Status Legend: |  | Green — On Track | Amber — At Risk | Red — Blocked | Not Started
Workstream | Milestone / Deliverable | Description | Status | Owner | Target Date | % Complete | Latest Update | Blockers / Risks
Tagging & Naming Conventions | Define Resource Tagging Standard | Establish mandatory + optional tags (Environment, Owner, CostCenter, Application, CMMC-Level, Terraform-Managed, etc.) | Not Started | TBD |  | 0% | Needs alignment across teams before any resources are deployed
| Define Naming Conventions | Standardized naming patterns for accounts, VPCs, subnets, EKS clusters, IAM roles, S3 buckets, etc. | Not Started | TBD |  | 0% | Document conventions and encode in TF modules as defaults
| Tag Enforcement Policy | AWS Config rules or SCPs to deny untagged resource creation; CI lint checks in GitHub Actions | Not Started | TBD |  | 0% | Enforce via SCP + AWS Config after conventions are approved
Bootstrap TF Module | OIDC Provider for GitHub Actions | Configure AWS IAM OIDC identity provider to allow GitHub Actions workflows to assume roles without long-lived credentials | Not Started | TBD |  | 0%
| Terraform State Backend (S3 + DynamoDB) | S3 bucket (versioned, encrypted, logging) + DynamoDB table for state locking per account | Not Started | TBD |  | 0%
| IAM Roles & Policies for TF Execution | Least-privilege execution roles for GH Actions (plan role, apply role); boundary policies | Not Started | TBD |  | 0%
| GitHub Actions Workflow Templates | Reusable GHA workflows for terraform init/plan/apply with OIDC auth, state locking, PR-based plan output | Not Started | TBD |  | 0%
| Bootstrap Module Documentation & Runbook | README + runbook for onboarding new accounts through the bootstrap module | Not Started | TBD |  | 0%
Account Vending Machine | Account Vending Design & Approval | Architecture for automated account provisioning: Org API / TF module to create accounts under correct OU with baseline SCPs | Not Started | TBD |  | 0%
| Account Baseline TF Module | Module that applies to every new account: bootstrap (OIDC, state), security baseline, networking attachment, tagging | Not Started | TBD |  | 0%
| OU Structure & SCP Assignment | Define OU hierarchy (Prod, Non-Prod, Sandbox, Security, Shared Services) + attach appropriate SCPs per OU | Not Started | TBD |  | 0%
| Account Request & Provisioning Workflow | Intake process (form/ticket/PR) that triggers GHA pipeline to vend a fully baselined account end-to-end | Not Started | TBD |  | 0%
IAM Identity Center (SSO) | Enable IAM Identity Center | Enable in the management or delegated admin account; select identity source (built-in, AD, or external IdP) | Not Started | TBD |  | 0% |  | Pending decision on IdP (Okta / Azure AD / built-in)
| IdP Integration / Federation | SAML/SCIM integration with corporate IdP for automated user & group provisioning | Not Started | TBD |  | 0%
| Permission Sets Design | Define permission sets (Admin, PowerUser, ReadOnly, DevOps, SecurityAudit, etc.) mapped to job functions | Not Started | TBD |  | 0%
| Account Assignments | Map groups → permission sets → accounts; automate via Terraform aws_ssoadmin resources | Not Started | TBD |  | 0%
| MFA Enforcement & Session Policies | Require MFA for all SSO users; configure session duration and re-auth policies | Not Started | TBD |  | 0%
Security Account Setup | Designate Security Tooling Account | Dedicated account under the Org for centralized security services (delegated admin where supported) | Not Started | TBD |  | 0%
| GuardDuty — Org-wide Enablement | Enable GuardDuty with delegated admin in Security account; auto-enable for new accounts; configure findings export to S3 | Not Started | TBD |  | 0%
| AWS Config — Org Aggregator | Enable Config in all accounts/regions; aggregator in Security account; deploy conformance packs (CIS, CMMC) | Not Started | TBD |  | 0%
| CloudTrail — Org Trail | Organization-level trail logging all management + data events to centralized S3 bucket in Security account | Not Started | TBD |  | 0%
| CloudWatch — Cross-Account Observability | Monitoring account config; cross-account sharing for metrics, logs, and traces from member accounts | Not Started | TBD |  | 0%
| Security Hub — Central Findings | Enable Security Hub with delegated admin; aggregate findings from GuardDuty, Config, Inspector across Org | Not Started | TBD |  | 0%
| Alerting & Notification Routing | SNS topics + EventBridge rules for critical findings; route to PagerDuty / Teams / email | Not Started | TBD |  | 0%
Shared Network Setup | VPC Architecture & CIDR Planning | Hub-spoke VPC design; non-overlapping CIDR allocation across all accounts; IPAM pool setup | Not Started | TBD |  | 0%
| Transit Gateway (TGW) | Deploy TGW in shared networking account; route tables for prod/non-prod isolation; RAM sharing to member accounts | Not Started | TBD |  | 0%
| Subnet Design & Tiering | Public, private, data, and firewall subnet tiers per AZ; standardized TF module for consistent deployment | Not Started | TBD |  | 0%
| VPC Endpoints (PrivateLink) | Centralized VPC endpoints for S3, ECR, STS, SSM, CloudWatch, KMS, etc. shared via TGW or per-VPC | Not Started | TBD |  | 0%
| DNS Strategy (Route 53) | Private hosted zones per account; Route 53 Resolver rules for hybrid DNS; forwarding to on-prem if applicable | Not Started | TBD |  | 0%
| Network Firewall / NACLs | AWS Network Firewall in inspection VPC or NACLs + baseline security group templates | Not Started | TBD |  | 0%
| VPN / Direct Connect (if applicable) | Site-to-site VPN or DX for hybrid connectivity; attach to TGW | Not Started | TBD |  | 0%
EKS Baseline (CMMC Compliant) | EKS Cluster Provisioning (Terraform) | Shared EKS cluster via TF; private API endpoint; managed node groups; envelope encryption with KMS; CMMC-aligned config | Not Started | TBD |  | 0%
| EKS Pod Identity Agent | Deploy EKS Pod Identity agent add-on; configure pod identity associations for workloads to assume IAM roles without IRSA | Not Started | TBD |  | 0%
| Wiz Agent — K8s Runtime Connector | Deploy Wiz Kubernetes connector (DaemonSet) for runtime visibility, vulnerability scanning, and compliance posture | Not Started | TBD |  | 0%
| Cluster Networking (VPC CNI + Ingress) | AWS VPC CNI plugin config; ALB Ingress Controller or NGINX; network policies (Calico/Cilium) for namespace isolation | Not Started | TBD |  | 0%
| Cluster Logging & Audit | Enable control plane logging (API server, audit, authenticator); Fluent Bit DaemonSet for pod logs → CloudWatch / S3 | Not Started | TBD |  | 0%
| Image Security & ECR | Private ECR repos; image scanning on push; admission controller (Kyverno/OPA) to block unscanned or unsigned images | Not Started | TBD |  | 0%
| Secrets Management | AWS Secrets Manager CSI driver; KMS encryption; no secrets in env vars or ConfigMaps (CMMC req) | Not Started | TBD |  | 0%
| CIS / CMMC Hardening | CIS EKS Benchmark controls; CMMC Level 2 controls mapping (AC, AU, SC, SI families); Wiz + Config compliance checks | Not Started | TBD |  | 0%
Landing Zone Team Onboarding | GitHub Repo Provisioning (per team) | Automated creation of team repo from template; branch protection; GHA workflows pre-configured with OIDC + TF | Not Started | TBD |  | 0%
| K8s Namespace Provisioning | Dedicated namespace per team with labels and annotations for cost tracking and compliance | Not Started | TBD |  | 0%
| K8s RBAC (per team) | Namespace-scoped Roles + RoleBindings tied to IAM Identity Center groups via EKS access entries | Not Started | TBD |  | 0%
| Resource Quotas & Limit Ranges | ResourceQuota (CPU, memory, pod count, PVC) + LimitRange defaults per namespace to prevent noisy-neighbor issues | Not Started | TBD |  | 0%
| Network Policies (namespace isolation) | Default-deny ingress/egress per namespace; explicit allow rules for approved cross-namespace and external traffic | Not Started | TBD |  | 0%
| Team Onboarding Runbook & Self-Service | Documentation + intake form/PR template; one pipeline to vend repo + namespace + RBAC + quotas end-to-end | Not Started | TBD |  | 0%
Budget & Cost Management | AWS Budgets Setup | Account-level and OU-level budgets with alert thresholds (50%, 80%, 100%); notification to owners via SNS/email | Not Started | TBD |  | 0%
| Cost Allocation Tags | Activate cost allocation tags (CostCenter, Application, Team, Environment) in billing console for chargeback/showback | Not Started | TBD |  | 0%
| Cost Anomaly Detection | Enable AWS Cost Anomaly Detection monitors per account and service; route alerts to finance + engineering | Not Started | TBD |  | 0%
| Cost Explorer Dashboards | Saved Cost Explorer views for leadership: spend by account, service, team, environment; month-over-month trend | Not Started | TBD |  | 0%
| FinOps Review Cadence | Establish monthly cost review meeting; define optimization targets (RI/SP coverage, idle resources, right-sizing) | Not Started | TBD |  | 0%